## Year 2023
Yearly Plan 2023
Quarterly Plan Q1
Week | Task | Release # | Estimation (hours) | Status
2023-01-16 | Work thorugh | 0.1.0 | 2 | Done
2023-01-23 | Continous delivery on azure | 0.2.0 | 5 | Done
2023-01-30 | Deploy Flask starter code | 0.3.0 | 2 | Done
2023-02-06 | Make predictions | 0.4.0 | 4 | Done
2023-02-13 | Logs | 0.5.0 | 3 | Done
2023-02-20 | Loadtest with locust | 0.6.0 | 4 | Done
2023-02-27 | Azure CLI to deploy and manage | 0.6.0 | 3 | Done
2023-03-06 | Documentation | 0.7.0 | 6 | Done
2023-03-13 | Demo | 0.8.0 | 4 | Done
2023-03-20 | Demo | 1.0.0 | 4 | Done
2023-03-27 | QA Testing Done | 1.1.0 | 3 | Done
2023-04-03 | Fix bugs | 1.1.1 | 10 | Done
Top 3 Quarter Goals | Order Prioritized Features | Proposed Difficulty 1-3 (1 easy and 3 is tough) | Feature Category | Project Management Guidelines
Stick to the plan | Udacity learning | 3 | Media | Project research
Work on project daily |  | 2 | Bash | Learn udacity chapters
Log into udacity every day |  | 2 | Azure | Get work done in order get time for udacity
|  | 1 | Bash
|  | 2 | Python
Quarterly Plan Q2
Week | Task | Release # | Estimation (hours) | Status
2023-04-10 | Checkout git repo C1 | 1.1.2 | 1 | Done
2023-04-17 | Create reusable cloud infrastructure | 1.1.3 | 2 | Done
2023-04-24 | Use automation tools for the creation of Azure IaaS | 1.1.4 | 3 | Done
2023-05-01 | Configure components of cloud system | 1.1.5 | 5 | Done
2023-05-08 | Use Terraform for the creation of Azure resources | 1.1.6 | 4 | Done
2023-05-15 | Use Packer for the creation of Azure IaaS services | 1.1.7 | 4 | Done
2023-05-22 | Azure CLI to deploy and manage | 1.1.8 | 3 | Done
2023-05-29 | Documentation | 1.1.9 | 7 | Done
2023-06-05 | Demo | 1.2.0 | 3 | Done
2023-06-12 | Demo | 1.2.1 | 3 | Done
2023-06-19 | QA Testing Done | 1.2.2 | 3 | Done
2023-06-26 | Fix bugs | 1.2.3 | 10 | Done
Top 3 Quarter Goals | Order Prioritized Features | Proposed Difficulty 1-3 (1 easy and 3 is tough) | Feature Category | Project Management Guidelines
Stick to the plan | Demo | 3 | Media | Demo last day of every sprint
Work on project daily | Documentation | 3 | Bash | Bi-Weekly planning after demo
Finish project weeks before deadline | Deployment | 2 | Azure | Release every 2 weeks
| Initial project setup | 1 | Bash | Tickets are estimated in hours of work
| Packer image | 3 | Azure
Quarterly Plan Q3
Week | Task | Release # | Estimation (hours) | Status
2023-07-03 | Checkout git repo C2 | 1.2.3 | 2 | Done
2023-07-10 | Continous delivery on azure | 1.2.4 | 5 | Done
2023-07-17 | Deploy Flask starter code | 1.2.5 | 2 | Done
2023-07-24 | Make predictions | 1.2.6 | 4 | Done
2023-07-31 | Logs | 1.2.7 | 3 | Done
2023-08-07 | Loadtest with locust | 1.2.8 | 4 | Done
2023-08-14 | Azure CLI to deploy and manage | 1.2.9 | 3 | Done
2023-08-21 | Documentation | 1.2.10 | 6 | Done
2023-08-28 | Demo | 1.3.0 | 30 | Done
2023-09-04 | Demo | 1.3.1 | 30 | Done
2023-09-11 | QA Testing Done | 1.3.2 | 3 | Todo
2023-09-18 | Fix bugs | 1.3.3 | 10 | Todo
Top 3 Quarter Goals | Order Prioritized Features | Proposed Difficulty 1-3 (1 easy and 3 is tough) | Feature Category | Project Management Guidelines
Stick to the plan | Demo | 3 | Media | Demo last day of every sprint
Work on project daily | Logging | 2 | Bash | Bi-Weekly planning after demo
Finish project weeks before deadline | Deployment | 2 | Azure | Release every 2 weeks
| Initial project setup | 1 | Bash | Tickets are estimated in hours of work
| Loadtest | 2 | Python
Quarterly Plan Q4
Week | Task | Release # | Estimation (hours) | Status
2023-09-25 | Checkout git repo C3 | 1.3.4 | 2 | Todo
2023-10-02 | Utilize Terraform to apply Infrastructure as Code | 1.3.5 | 5 | Todo
2023-10-09 | Add automated testing tasks | 1.3.6 | 2 | Todo
2023-10-16 | Design and run a load test suite post-deployment using JMeter | 1.3.7 | 4 | Todo
2023-10-23 | Design and run functional test suites | 1.3.8 | 3 | Todo
2023-10-30 | Design and run API-integration tests | 1.3.9 | 4 | Todo
2023-11-06 | Configure Azure Monitor to identify and mitigate operational issues | 1.3.10 | 3 | Todo
2023-11-13 | Configure Azure Log Analytics | 1.3.11 | 6 | Todo
2023-11-20 | Documentation | 1.3.12 | 4 | Todo
2023-11-27 | Demo | 1.3.13 | 4 | Todo
2023-12-04 | QA Testing Done | 1.3.14 | 3 | Todo
2023-12-11 | Fix bugs | 1.3.15 | 10 | Todo
Top 3 Quarter Goals | Order Prioritized Features | Proposed Difficulty 1-3 (1 easy and 3 is tough) | Feature Category | Project Management Guidelines
Stick to the plan | Demo | 3 | Media | Demo last day of every sprint
Work on project daily | Logging | 2 | Bash | Bi-Weekly planning after demo
Finish project weeks before deadline | Deployment | 2 | Azure | Release every 2 weeks
| Initial project setup | 1 | Bash | Tickets are estimated in hours of work
| Loadtest | 2 | Python